## Sheet1
Risk ID | Risk Title | Risk Description | Related Control Gap | Asset | Likelihood | Impact | Risk Score | Rating | Recommended Remediation | Status
R-001 | Unauthorized External Access | Public network exposure could increase the possibility of unauthorized access to company storage and potential exposure of company data. | Public network access enabled from all networks | Azure Storage Account | 3 | 5 | 15 | High | Disable unnecessary public network access and use authorized networks or private endpoints. | Open
R-002 | Shared Credential Compromise | Storage account keys are shared credentials that could be compromised or misused, potentially providing unauthorized access to storage resources. | Storage account key access enabled | Azure Storage Account | 2 | 4 | 8 | Medium | Use Microsoft Entra ID authentication with least-privilege Azure RBAC assignments and disable shared-key authorization where possible. | Open
R-003 | Delayed Threat Detection | Malicious activity involving storage resources may go undetected or experience delayed detection when storage-specific threat monitoring is unavailable. | Defender for Storage initially disabled | Azure Storage Account | 3 | 5 | 15 | High | Enable Microsoft Defender for Storage and review generated security alerts. | Remediated
R-004 | Insufficient Forensic Evidence | Security-relevant storage activity may not be adequately captured, limiting the organization's ability to investigate incidents and reconstruct events. | Diagnostic settings disabled | Azure Storage Account | 4 | 2 | 8 | Medium | Enable diagnostic settings and send relevant logs to a centralized logging destination. | Open
R-005 | Accidental Data Overwrite | Important Blob data could be accidentally overwritten or modified without the ability to easily restore a previous version. | Blob versioning disabled | Blob Storage | 4 | 3 | 12 | High | Enable Blob versioning and establish an appropriate version-retention policy. | Open
R-006 | Accidental Resource Deletion | An authorized administrator could accidentally delete the Storage Account because deletion protection is not configured. | No resource lock | Azure Storage Account | 2 | 5 | 10 | High | Apply a CanNotDelete resource lock to critical storage resources. | Open
R-007 | Reduced User Accountability | Reliance on shared-key authorization may make storage activity more difficult to attribute to an individual user. | Storage account key access enabled | Azure Storage Account | 4 | 3 | 12 | High | Use Microsoft Entra ID authentication and individual least-privilege Azure RBAC assignments. | Open
R-008 | Delayed Incident Response | Insufficient diagnostic logging could delay incident identification, scoping, containment, and response. | Diagnostic settings disabled | Azure Storage Account | 3 | 4 | 12 | High | Enable diagnostic logging and centralize relevant logs for security monitoring and incident response. | Open
R-009 | Malicious Data Modification | A compromised or authorized account could intentionally modify important Blob data without an easy method of restoring previous versions. | Blob versioning disabled | Blob Storage | 2 | 3 | 6 | Medium | Enable Blob versioning and configure appropriate retention settings. | Open
R-010 | Automated Bot Scanning | Publicly reachable cloud storage endpoints may be discovered and probed by automated scanners, increasing exposure to reconnaissance and attempted unauthorized access. | Public network access enabled from all networks | Azure Storage Account | 3 | 4 | 12 | High | Restrict public network access and use authorized networks or private endpoints where appropriate. | Open
R-011 | Unscanned Malicious Uploads | Files uploaded to Blob Storage may not be automatically scanned for malware, potentially allowing malicious files to be stored and later accessed or distributed. | On-upload malware scanning disabled | Blob Storage | 2 | 5 | 10 | High | Enable on-upload malware scanning in Microsoft Defender for Storage where appropriate. | Open
R-012 | Replication and Version Recovery Limitations | Lack of Blob versioning reduces version-history protection and may complicate recovery or workflows that rely on maintaining previous object states. | Blob versioning disabled | Blob Storage | 2 | 3 | 6 | Medium | Enable Blob versioning and establish appropriate lifecycle and retention settings. | Open
R-013 | Unresolved Policy Noncompliance | Azure Policy findings may remain unresolved, allowing insecure or non-standard resource configurations to persist. | Azure Policy reported non-compliant policies | Azure Subscription | 3 | 3 | 9 | Medium | Review non-compliant policies, prioritize applicable findings, remediate configurations, and document justified exceptions. | Open
R-014 | Costly Service Disruption | Accidental deletion of an essential storage resource could cause prolonged downtime while administrators recover or rebuild affected resources. | No resource lock | Azure Storage Account | 2 | 5 | 10 | High | Apply a CanNotDelete resource lock and maintain tested recovery procedures. | Open
R-015 | Accidental Shared-Key Exposure | Storage account keys could be exposed through source code, scripts, configuration files, logs, documentation, or improper sharing, potentially allowing unauthorized storage access. | Storage account key access enabled | Azure Storage Account | 3 | 4 | 12 | High | Use Microsoft Entra ID with Azure RBAC and disable shared-key authorization where it is not required. | Open